## RAID Log
RAID Log — [Project Name]
Risks, Assumptions, Issues, Dependencies ¦ Owner: [Program Manager] ¦ Last reviewed: [date]
ID | Category | Description | Date Raised | Owner | Probability (1-5) | Impact (1-5) | Priority Score | Status | Mitigation / Response Plan | Target Date | Days Open | Last Updated | Notes
R-001 | Risk | Vendor may not deliver API access before sprint 12 start | 2026-08-04 | Asha Veerpaneni | 3 | 4 | 12 | Monitoring | Weekly check-in with vendor PM; fallback mock endpoint ready if slip confirmed by Aug 20 | 2026-09-03 | 10 | 2026-08-13 | Escalate to Sponsor if unresolved by target date
A-002 | Assumption | Assuming Team Bravo's test environment will be ready by sprint start | 2026-08-07 | Marcus Cho | 2 | 3 | 6 | Open | Confirm with infra team by Aug 18; adjust sprint scope if assumption is false | 2026-08-20 | 7 | 2026-08-12 | Not yet validated
I-003 | Issue | Notification service memory leak causing intermittent outages | 2026-08-11 | Priya Nair |  | 5 |  | Escalated | Hotfix in progress; rollback plan ready if not resolved by end of week | 2026-08-16 | 3 | 2026-08-14 | Escalated to Engineering Director on Aug 12
D-004 | Dependency | Reporting dashboard migration depends on Data Platform team's pipeline API | 2026-07-31 | Dana Lee | 2 | 4 | 8 | Open | Dependency confirmed on Data Platform's roadmap for Aug 25; tracking via their JIRA | 2026-08-29 | 14 | 2026-08-13 | No slippage reported yet
Formulas:
Days Open = IF([Status]="Closed","",TODAY()-[Date Raised])
Days Open = IF([Status]="Closed","",IF([Date Raised]="","",TODAY()-[Date Raised]))

## Legend
How to use this RAID log
Category | Risk = might happen and would hurt the project. Assumption = treated as true, unvalidated. Issue = already happening, needs active resolution. Dependency = something outside your control that you're relying on.
Probability / Impact | Rate 1 (low) to 5 (high). For Risks, Probability = likelihood it occurs; Impact = damage if it does. For Issues, leave Probability blank and rate Impact as current severity. For Assumptions/Dependencies, use both to reflect how critical the item is if it goes wrong.
Priority Score | Calculated automatically as Probability x Impact. 15+ = high priority (red), 8-14 = medium (orange), below 8 = low (no highlight).
Status | Open = logged, not yet actively managed. Monitoring = being watched, no action needed yet. Escalated = needs leadership attention now. Closed = resolved.
Days Open | Calculated automatically from Date Raised. Blank once Status is set to Closed.
Yellow-shaded rows | Blank rows ready for you to fill in — replace the shading once populated if you prefer a cleaner look.
Recommended cadence | Review weekly as a standing agenda item. Anything Escalated or open >14 days should be called out explicitly to stakeholders, not buried in the full log.
Log discipline — rules to follow
One category at a time | A risk that materializes becomes an Issue, not both — update the existing row's Category and Status rather than creating a duplicate entry. Same for an assumption that turns out false: convert it to an Issue (if it already caused harm) or a Risk (if it's now a known future concern).
One named owner per entry | Never a team or department name. "Engineering" isn't accountable; a specific person is. Reassign explicitly if ownership changes — don't leave it blank.
No entry without a plan | A Risk or Issue needs a mitigation or response plan before it's considered logged, not just a description of the problem. A Dependency needs a specific date and named source. An Assumption needs a validation date.
Never delete — close instead | Closed items stay in the log with Status = Closed. Deleting loses the historical record of what was known and when, which matters for retrospectives and, in regulated environments, for audits.
Log status changes, don't silently overwrite | When a score or status changes, update Last Updated so there's a visible trail of when something got better or worse — not just its current state.
Separate sensitive items if sharing broadly | If this log goes to external stakeholders or a wide audience, keep anything sensitive (vendor pricing, personnel issues, legal exposure) in a restricted version instead of the general-access log.